## Full_Plan
Phase | Task ID | Task Name | Description | Developer Role | Priority | Est. Hours | Dependencies | Status | Deliverables
Phase 1: Core Compliance & EMR Engine | T1.1 | EMR Database Schema Design (PDPL) | Design secure, offline-first database schema (PostgreSQL) accounting for PDPL's data residency, patient consent, and mandatory audit trail requirements. | Lead Backend | High | 20 |  | Not Started | Schema SQL, Migration scripts, Data Residency Plan (Document)
Phase 1: Core Compliance & EMR Engine | T1.2 | Local Cloud Hosting Setup (PDPL) | Configure dedicated secure hosting infrastructure with a local provider (e.g., Telecom Egypt) ensuring strict compliance with PDPL data residency requirements. | Lead Backend | High | 24 | T1.1 | Not Started | Cloud architecture diagram, VPN/Firewall configuration, Residency certification.
Phase 1: Core Compliance & EMR Engine | T1.3 | DICOM/Media Upload & Storage API | Build system to securely upload, encrypt, and store large medical files (DICOM images, X-rays) optimizing for low bandwidth/offline synchronization. | Lead Backend | High | 32 | T1.2 | Not Started | Secure Storage API, Encryption modules (AES-256), Offline sync protocol.
Phase 1: Core Compliance & EMR Engine | T1.4 | Medical Terminology Vector DB Setup | Set up a Vector Database (Qdrant/Chroma) to index national clinical guidelines and ICD-11/SNOMED codes relevant to the Egyptian disease profile. | Lead Backend | High | 16 | T1.1 | Not Started | Vector DB instance, ICD-11/SNOMED index, Connection utilities.
Phase 1: Core Compliance & EMR Engine | T1.5 | Knowledge Base Embedding Generation | Implement embedding generation for medical literature, symptom descriptions, and common Egyptian treatment protocols for AI retrieval. | Lead Backend | High | 20 | T1.4 | Not Started | Embedding pipeline, Batch processing script, Knowledge base integration.
Phase 1: Core Compliance & EMR Engine | T1.6 | Core EMR API (Patient/Visit CRUD) | Create basic REST endpoints for patient registration, visit logs, and simple demographic data management. Implement input validation. | Junior Backend | High | 24 | T1.1 | Not Started | FastAPI routes for CRUD, Basic unit tests, Postman documentation.
Phase 1: Core Compliance & EMR Engine | F1.1 | EMR Portal Setup & Architecture | Initialize React/Next.js Doctor Portal with TypeScript, configure responsive folder structure, and secure authentication flow scaffolding. | Junior Frontend | High | 12 |  | Not Started | React project structure, Auth component placeholder, Theme config.
Phase 1: Core Compliance & EMR Engine | F1.2 | Patient Registration UI | Build the user interface for inputting and validating new patient demographic information and consent forms. | Junior Frontend | High | 20 | F1.1, T1.6 | Not Started | Patient form component (validated), PDPL consent UI, API consumption logic.
Phase 1: Core Compliance & EMR Engine | T1.7 | AI Model Setup for Diagnosis V1 | Set up a clinical LLM (e.g., fine-tuned LLaMA) inference server for initial symptom triage and basic differential diagnosis suggestions. | Lead Backend | High | 28 | T1.5 | Not Started | LLM inference server, API wrapper, Initial prompt templates (English/Arabic).
Phase 1: Core Compliance & EMR Engine | T1.8 | Audit Log Pipeline | Implement mandatory, immutable logging for all read/write actions on sensitive patient data as required by PDPL. | Lead Backend | High | 20 | T1.1 | Not Started | Centralized log service, Immutable log format, Audit Log API endpoints.
Phase 1: Core Compliance & EMR Engine | T1.9 | Offline Data Sync Protocol V1 | Develop the core logic for secure, bidirectional data synchronization (optimizing for weak Egyptian internet) and conflict resolution. | Lead Backend | High | 24 | T1.8 | Not Started | Sync logic module, Conflict resolution algorithm, Test suite for offline use.
Phase 1: Core Compliance & EMR Engine | F1.3 | Dashboard & Navigation UI | Create the main doctor dashboard UI, navigation structure, and responsive layout for EMR access. | Junior Frontend | Medium | 16 | F1.2 | Not Started | Main layout component, Sidebar navigation, Route setup.
Phase 2: Telehealth & Patient Experience | T2.1 | Encrypted WebRTC Telehealth Infrastructure | Set up WebRTC signaling server (coturn/Janus) with end-to-end encryption for live consultations, ensuring compliance with local communication privacy laws. | Lead Backend | High | 32 | T1.9 | Not Started | WebRTC server, Signaling service, Encryption key management, TURN/STUN configuration.
Phase 2: Telehealth & Patient Experience | T2.2 | Patient Identity Verification API | Implement a secure API for Doctor and Patient 2FA and identity verification required before starting a Telehealth session (Mandatory for EDA compliance). | Lead Backend | High | 24 | T2.1 | Not Started | Verification API, OTP generation/validation service, Session token management.
Phase 2: Telehealth & Patient Experience | T2.3 | Prescription & Drug CRUD API | Build basic APIs for adding, retrieving, and updating electronic prescriptions and drug entries (Generic drugs first). | Junior Backend | Medium | 20 | T1.6 | Not Started | Prescription API endpoints, Validation logic, Drug dictionary service setup.
Phase 2: Telehealth & Patient Experience | T2.4 | E-Prescription Form UI | Develop the front-end form for doctors to create new prescriptions with drug search functionality and validation rules. | Junior Frontend | Medium | 16 | F1.3, T2.3 | Not Started | Prescription form component, Drug search UI, Form validation library integration.
Phase 2: Telehealth & Patient Experience | F2.1 | Telehealth Video/Audio UI | Integrate WebRTC client functionality into the Patient Portal/Doctor Portal for live video and audio streaming during consultation. | Junior Frontend | High | 28 | F1.3, T2.1 | Not Started | Video components, Peer connection logic, Device selector.
Phase 2: Telehealth & Patient Experience | T2.5 | Telehealth Session Recording Backend | Implement secure, encrypted backend storage and APIs for optional consultation session recording (with clear patient consent protocols). | Lead Backend | Medium | 16 | T1.3, T2.1 | Not Started | Recording service, Encrypted storage utility, Playback API.
Phase 2: Telehealth & Patient Experience | F2.2 | Shared EMR Viewer UI | Create a split-screen or overlay UI that allows the doctor and patient to view relevant parts of the EMR during the Telehealth call. | Junior Frontend | High | 20 | F2.1 | Not Started | Layout component, Data sharing panel, Read-only EMR view.
Phase 2: Telehealth & Patient Experience | T2.6 | EDA Registration Documentation Prep | Prepare all technical and operational documentation required for initial registration as medical software with the Egyptian Drug Authority (EDA). | Lead Backend | High | 40 | T1.8 | Not Started | Technical file draft, Risk management plan (Document), Software classification report.
Phase 3: Clinical Decision Support (CDS) V1 | T3.1 | CDS Retrieval Engine (RAG) | Implement the core RAG logic for the AI assistant to retrieve relevant clinical guidelines and medical literature based on patient symptoms and EMR context. | Lead Backend | High | 28 | T1.7, T1.5 | Not Started | RAG query pipeline, Context window optimization, Retrieval metrics tracking.
Phase 3: Clinical Decision Support (CDS) V1 | T3.2 | Diagnosis Suggestion Pipeline | Build the LLM pipeline that takes EMR context and RAG results to generate differential diagnosis suggestions and confidence scores. | Lead Backend | High | 24 | T3.1 | Not Started | Prompt templates (clinical), Generation API, Confidence scoring logic.
Phase 3: Clinical Decision Support (CDS) V1 | T3.3 | CDS Quality Gate (Accuracy Check) | Implement a quality gate using FactScore or similar validation against the structured knowledge base to prevent clinical hallucinations (Critical Safety Feature). | Lead Backend | High | 20 | T3.2 | Not Started | Quality gate system, Verification layer, Safety threshold checker.
Phase 3: Clinical Decision Support (CDS) V1 | T3.4 | EMR Data Structuring API (FHIR/HL7) | Develop an API to structure unstructured clinical notes (triage notes, history) into a standardized format (FHIR/HL7 light) for better CDS input. | Junior Backend | Medium | 20 | T1.6 | Not Started | Structuring API, NLP parser integration, Validation.
Phase 3: Clinical Decision Support (CDS) V1 | F3.1 | Symptom Capture UI | Create interactive forms for structured input of patient symptoms, history, and vital signs. | Junior Frontend | High | 20 | F1.3, T3.4 | Not Started | Symptom checker component, Input validation, Data binding to T3.4.
Phase 3: Clinical Decision Support (CDS) V1 | F3.2 | AI Diagnosis Suggestion Display | Build the UI component to display AI diagnosis suggestions, confidence scores, and links to the supporting RAG evidence (must be clearly marked as 'Assistant'). | Junior Frontend | High | 16 | F3.1, T3.3 | Not Started | Suggestion display component, Evidence viewer, Disclaimer modal.
Phase 4: Drug Safety & Local Integrations | T4.1 | Drug-Drug Interaction (DDI) Logic | Implement a core engine using a knowledge graph (T4.2 dependency) to check for critical drug-drug interactions, drug-allergy, and drug-condition contraindications. | Lead Backend | High | 32 | T4.2 | Not Started | DDI algorithm, Alerting logic, Severity ranking system.
Phase 4: Drug Safety & Local Integrations | T4.2 | Drug Interaction Knowledge Graph Setup | Build and populate a structured knowledge graph (Neo4j/Postgres) linking Egyptian drug formulary, common allergies, and clinical conditions. | Lead Backend | High | 28 | T2.3 | Not Started | Knowledge graph schema, Formulary ingestion tool, Relationship mapping.
Phase 4: Drug Safety & Local Integrations | T4.3 | Fawry/Meeza Payment API Integration | Integrate a local Egyptian payment gateway (Fawry/Meeza) into the billing module for clinic service payments (non-patient portal side). | Junior Backend | High | 20 | T1.6 | Not Started | Payment API client, Transaction processing endpoints, Success/Failure handling.
Phase 4: Drug Safety & Local Integrations | T4.4 | E-Prescription Safety Check Alert UI | Create a mandatory alert modal/sidebar UI that intercepts prescription creation to display T4.1 DDI and contraindication warnings. | Junior Frontend | High | 16 | F2.4, T4.1 | Not Started | Safety alert modal, Warning indicator, Override justification capture.
Phase 4: Drug Safety & Local Integrations | T4.5 | Lab Report Parsing & Structuring | Implement automated parsing and data extraction from common Egyptian lab report formats (PDF/Image) using PyMuPDF and OCR, mapping results to structured EMR fields. | Lead Backend | Medium | 24 | T1.3 | Not Started | OCR/Parsing pipeline, Result normalization, Mapping dictionary.
Phase 4: Drug Safety & Local Integrations | F4.1 | Billing & Invoicing UI | Build the basic user interface for generating invoices, logging cash/card payments, and integrating the local payment status (T4.3). | Junior Frontend | Medium | 16 | F1.3, T4.3 | Not Started | Invoice generator component, Payment status display, Transaction log view.
Phase 5: Production & GTM Prep | T5.1 | End-to-End Security Audit & Pentest | Hire external security firm to conduct a comprehensive security review and penetration test focusing on PDPL compliance, Telehealth encryption, and data segregation. | Lead Backend | High | 40 | T4.1, T2.2 | Not Started | Security audit report, Vulnerability patch implementation, Final compliance certification.
Phase 5: Production & GTM Prep | T5.2 | Performance Tuning & Load Testing | Optimize API response times, database queries, and AI inference latency. Conduct load tests simulating 10x target clinics. | Lead Backend | High | 32 | T1.9, T3.3 | Not Started | Performance benchmarks (Latency < 500ms), Load test results, Query optimization scripts.
Phase 5: Production & GTM Prep | T5.3 | CI/CD & Automated Deployment | Implement production-ready CI/CD pipelines (GitLab/GitHub Actions) for zero-downtime deployment, automated testing, and rollbacks. | Lead Backend | Medium | 20 | T1.9, T5.2 | Not Started | CI/CD pipeline config, Automated rollback mechanism, Monitoring setup (Prometheus/Grafana).
Phase 5: Production & GTM Prep | T5.4 | Doctor Training & Onboarding Material | Create comprehensive guides, video tutorials, and technical support documentation for EMR usage, Telehealth, and AI features. | Junior Frontend | Medium | 24 | F4.1 | Not Started | User manuals (Arabic/English), Training video scripts, FAQ library.
Phase 5: Production & GTM Prep | T5.5 | Final EDA Submission & Compliance Checklist | Finalize and submit all documentation (T2.6) to the Egyptian Drug Authority and ensure the system meets all final technical criteria for commercial operation. | Lead Backend | High | 36 | T5.1, T2.6 | Not Started | Official EDA submission, Regulatory feedback tracking, Compliance sign-off.
Phase 5: Production & GTM Prep | F5.1 | Final Responsive & Accessibility Review | Conduct final UI/UX review for responsiveness on tablets/desktop and ensure basic WCAG accessibility compliance for the Egyptian market. | Junior Frontend | Medium | 16 | F4.4 | Not Started | Accessibility report, Final design review sign-off, Mobile/Tablet layout fixes.

## الورقة1
هذا يبدو مشروعًا ممتازًا وقويًا جدًا لحافظة الأعمال! إليك خطة مفصلة ومنظمة في شكل جدول، مستوحاة من هيكل الجدول الذي تعرضه، لتحويل خريطة الطريق الخاصة بك إلى مهام قابلة للتنفيذ:
Phase | Task ID | Task Name | Description | Developer Role | Priority | Est. Hours | Dependencies | Status | Deliverables | Done
Phase 1: Data & Baseline | T1.1 | Data Acquisition & Setup | Download the Kaggle Credit Card Fraud Dataset and initialize the project environment (Notebooks, dependencies). | Data Scientist | High | 4 |  | Not Started | Project Structure, Initial Data Load Script
Phase 1: Data & Baseline | T1.2 | Exploratory Data Analysis (EDA) | Analyze class distribution, perform correlation analysis, detect outliers, and determine initial feature importance. | Data Scientist | High | 8 | T1.1 | EDA Notebook (High-quality), Key Insights Document
Phase 1: Data & Baseline | T1.3 | Feature Engineering & Scaling | Apply Stratified split, implement data scaling (StandardScaler), and prepare feature sets for training. | Data Scientist | High | 6 | T1.2 | Scaled Feature DataFrames, Split Strategy Definition
Phase 1: Data & Baseline | T1.4 | Baseline Model Training (LR) | Train a Logistic Regression model as the baseline, focusing on ROC-AUC, PR-AUC, F1, and Confusion Matrix. | Data Scientist | High | 6 | T1.3 | Baseline Model Object (joblib), Performance Metrics Report (Baseline)
Phase 2: Advanced Modeling & Optimization | T2.1 | Advanced Model Training (XGBoost) | Train XGBoost model using cross-validation and hyperparameter tuning (e.g., Optuna/GridSearch). | Data Scientist | High | 10 | T1.3 | Trained XGBoost Model, Tuning Results Report
Phase 2: Advanced Modeling & Optimization | T2.2 | Advanced Model Training (LightGBM) | Train LightGBM model using cross-validation and hyperparameter tuning. | Data Scientist | High | 10 | T1.3 | Trained LightGBM Model, Tuning Results Report
Phase 2: Advanced Modeling & Optimization | T2.3 | Imbalance Handling Implementation | Implement and test strategies like SMOTE, class_weight, and threshold tuning. | Data Scientist | High | 8 | T2.1, T2.2 | Imbalance Handling Code, Strategy Comparison Metrics
Phase 2: Advanced Modeling & Optimization | T2.4 | Cost-Benefit Analysis & Threshold Tuning | Define business cost matrix (FN vs. FP) and tune the final classification threshold to minimize overall financial loss. | Data Scientist | High | 6 | T2.3 | Optimal Threshold Value, Cost Analysis Documentation
Phase 3: Explainability & Deployment | T3.1 | Model Explainability (SHAP) | Generate Global feature importance and Local explanations for specific fraud cases using the SHAP library. | Data Scientist | High | 8 | T2.4 | SHAP Analysis Notebook, Explanation Visualizations
Phase 3: Explainability & Deployment | T3.2 | API Development (FastAPI) | Build the FastAPI application with a /predict endpoint, ensuring the final best model is loaded (joblib). | MLOps Engineer | High | 12 | T2.4 | FastAPI App Code, Model Serialization (joblib)
Phase 3: Explainability & Deployment | T3.3 | Containerization (Docker) | Create a production-ready Dockerfile to containerize the FastAPI application and all dependencies. | MLOps Engineer | Medium | 6 | T3.2 | Dockerfile, Local Image Build Test
Phase 3: Explainability & Deployment | T3.4 | Deployment (Render/Railway) | Deploy the Dockerized application to a cloud platform (Render or Railway) for public access. | MLOps Engineer | Medium | 8 | T3.3 | Live API Endpoint URL, Deployment Configuration Files
Phase 3: Explainability & Deployment | T3.5 | Portfolio Documentation & Clean-up | Create a high-quality README, architecture diagram, and write detailed explanations on model choice (XGBoost win), threshold change, and business impact. | Data Scientist | High | 10 | T3.1, T3.4 | Comprehensive README, Architecture Diagram, Project Screenshots